## Tech Development Meeting on 14
Tech Development Meeting on 14 Feb 2020
Date | 14 Feb 2020 12:00(Beijing)—11:00
Meeting Topic | To discuss the tech development requirements
Recorder | Annalise
Participant | Voralak, Rittawee, Eak, Skura, Caroline, Haifeng, Annalise
Topic 1 | SCG agreed the timeline of system development and its quotation
Topic 2 | SCG confirmed his team will develop the apps, and provide detailed tech requirement within next 2 weeks, B-Tree requires to discuss app requirement with SCG’s app team
Topic 3 | Two party continue discuss tech development contract before providing app requirement
To-Do List
For SCG | No. | Deadline | Content
| 1 | 14 Feb-28 Feb | Provide detailed tech requirement within next 2 weeks, B-Tree requires to discuss app requirement with SCG’s app team
| 2. | - | Provide tech development contact template if possible
For B-tree | 1. |  | Fill the project form
| 2. |  | Offer timeline for development
| 3 |  | Provide scope/detail of tech development contract
| 4 |  | Next meeting will be hold between 22-25 Feb to discuss next B-Tree coming schedule (install BG0001)

## 20200214内部讨论(保密文档)
与app相关的思考点
1 | 系统开发预留端口给App(泰国自己开发), 单独列出来
2 | 留出端口给自己的App
2 | 国际版App海外登陆问题
与系统开发相关的思考点
1 | “个性化”暂时不做, 代价太大
2 | 信息错误类
3 | 第三方支付接口的API | 等泰国回复再评估可做性

## 12月5日-讨论前的表格
H =< 6M / M < 12M / L > 12M
Module | Function |  | Explanation | SCG suggested Priority (H/M/L) | B-Tree suggested Priority (H/M/L)
OPS/运管系统
User 用户 | User management 用户管理 | Add/update/delete user 人员管理：新增、更新、删除 | To Operators/针对运营人员 | H | H
|  | Password management 密码管理 | To Operators/针对运营人员 | H | H
|  | Role Permission 角色管理/权限管理 | To Operators/针对运营人员 | H | H
Box 盒子 | Box management 运营盒子管理 | Add/delete box 增加/删除盒子 |  | H | H
|  | Suspend box = Box status 盒子运营管理：待业、营业、停业、暂停营业 |  | H | H
|  | Location 盒子位置 |  | H | H
|  | Emergency handling-- 盒子紧急故障处理 |  | H | H
|  | Price Tag Electronics 电子价签 | Depends on PT hardwards/依赖于电子价签硬件 | M | L
|  | Advertising VDO 视频广告管理，可根据需要设置广告视频播放内容 |  | M | L
Commodity 商品 | Commodity 商品管理 | Add/update/delete product 商品增加、删除、更新 | To Products List/针对商品列表 | H | H
|  | Category 商品目录，针对泰国商品可配置 |  | H | H
|  | Hold product 商品库存管理 |  | H | H
|  | Maintain pricing 商品价格管理 * Price adjustment (advance) / 定时定价策略(烟酒类商品） |  | H | H
| Purchase order 采购管理 | Supplier Manage：Add/update/delete 供应商管理：新增、更新、删除 |  | H | H
|  | Costing by Supplier 供应商商品及进价管理 |  | H | H
|  | Purchase order process* ( Add Product … ) 进货订单/退货订单处理 |  | H | H
| Warehouse management 库存管理 | Stock availability 有效商品库存 |  | H | H
|  | Min stock 最小商品库存。用于安全库存报警，及时采购和补货 |  | H | H
|  | Reorder 重复订购 |  | H | H
|  | Good receive 商品入库 |  | H | H
|  | Good issue 入库商品问题处理 |  | H | H
|  | Inventory count 商品出入库数量 |  | H | H
|  | Damage/loss handling 盘点：盘亏/盘盈 | Connected with financial system/连接到财务系统 | H | H
|  | Stock adjustment 库存调整 | Connected with financial system/连接到财务系统 | H | H
| Return management 退货管理 | Return to supplier 退货(至供应商) | Option 1: Box return goods to supplier directly Option 2: Box return goods to warehouse, then warehouse return goods to supplier | H | H
| Inventory management 进销存管理（盒子） | Stock availability 盒子有效商品库存 |  | H | H
|  | Min stock 盒子最小库存 |  | H | H
|  | Reorder 盒子商品重复订购 |  | H | H
|  | Good receive 商品入盒 |  | H | H
|  | Good issue 入盒商品问题处理 |  | H | H
|  | Inventory count 商品库存 |  | H | H
|  | Damage/loss handling 盘点：盘亏/盘盈 |  | H | H
|  | Stock adjustment 商品库存微调 |  | H | H
Promotion 促销 | Promotion 促销 | Discount 折扣 |  | H | H
|  | Coupon 积分 |  | M | M
|  | Bonus 优惠券 |  | M | M
|  | Buy 1 Get 1 free : Get 2 Get 3 Get … 买1送N |  | H | H
|  | QR Promotion Discount |  | M
|  | Member Price by individual QR Code |  | M
|  | Limited Time by Product Ex. ALH 限时限价促销商品 |  | H | H
Financial Part 财务 | API Management 第三方系统对接 | Plug in with Netsuite 支持与SCG所用ERP系统（Netsuite）进行系统对接 |  | H | H
Owen | Owen function Owen相关 | Update program 收银软件更新 |  | H | M
|  | Support OS Window 10 支持Windows10 |  | H | M
|  | *Barcode management 增加Barcode识别功能，增强商品销售 |  | L | L
Security 商品防盗 | Security 商品防盗 | AM Tag AM标签 |  | H | H
Report 报告 | Transaction report 销售订单报告 | Daily, monthly 日报/月报 |  | H | M
|  | By location, By product category, By supplier 根据盒子/区域，商品分类，供应商等条件生成报告 |  | H | M
|  | Basket size, Avg. THB/bill 均单商品数，均单消费金额 |  | H | M
| Financial report 财务报告 | Revenue, Cost, Margin 收入报告、成本报告、毛利润报告 |  | H | M
|  | By location, By product category, By supplier 根据盒子/区域，商品分类，供应商等条件生成报告 |  | H | M
| Inventory report 进销存报告 | Stock 库存报告 |  | H | M
|  | Turnover 商品流转率 |  | H | M
|  | High/medium/slow move 高/中/低流转商品报告 |  | H | M
|  | Shelf life 商品保质期 |  | H | M
| Customer report 顾客报告 | Retention 顾客留存数据报告。顾客频次，回头率等 |  | M | M
|  | Personal; gender, demographic, spending 包含顾客数据：性别、国籍/地区、消费金额等 |  | M | M
| Customer support 客服报告 | Customer Incident report 客服问题处理报告 |  | H | M
| Operation Report 运营报告 | Operation Resolve report 运营问题处理报告。系统故障，运营故障等 |  | H | M
Language 系统语言 |  | English 英文支持 |  | H | H
Customer Service/客服系统
| Camera system 监控CCTV | Monitor 摄像头 | Not sure whether or not will we replace the entire CCTV module/不确定是否更换整个CCTV模块 | H | H
|  | Detection 人物动帧检测 | Depends on CCTV module/依赖于CCTV模块 | H | H
|  | Video playback 监控视频回放 | Depends on CCTV module/依赖于CCTV模块 | H | H
|  | APP Mobile 移动端视频查看功能 |  | H | M
| Blacklist 顾客黑名单 |  | To Customers/针对顾客 | H | H
| Logging system 客服日志系统 | Logging incident 客服日志系统 |  | H | M
| Call handling 客服呼叫调度 | 客服中心呼叫自动调度功能，多线顾客呼叫自动分配给不同客服 This function relate to Xiaoyu, SCG want to find local accessory to replace it. |  | H | L
| Remote control system 远程控制系统 | Communication with customer 语音/视频通话功能，与顾客进行通话 |  | H | H
|  | Open/Lock door remotely 远程开/关门 |  | H | H
|  | Control owen system; fix issue, restart system 远程控制Owen，解决问题，重启软件/PC |  | H | H
|  | Set alarm 与盒子里顾客通信，紧急情况下可呼叫到盒子并警告顾客 | Depends on hardwares/依赖于硬件 Now one can use video calls on screens inside boxes/目前可直接使用语音/视频电话接入到盒子内来实现 | H | M
|  | *Owen？？？?? |  | H
App/移动端
App | Register 注册 | By email, mobile no. 注册方式：E-Mail，手机号 |  | H | H
|  | OTP generation 短信验证 |  | H | H
| Login 登录 | Password Login 密码登录 |  | H | H
| Password management 密码管理 | Change/reset/forgot password * 修改密码 * 忘记密码找回 |  | H | H
| Opening door 开门 | QR Opening Door 扫码开门 |  | H | H
| Payment 支持方式 | TH QR |  | H | H
|  | ALIPAY |  | M | M
|  | LINE PAY |  | H | H
|  | Credit QR |  | H | H
|  | Face Payment 人脸支付 | Needs supports from hardwares/需要硬件设备支持 | M | L
| Search box 搜索附近的盒子 |  |  | L | M
| Search product availability 搜索盒子里商品 |  |  | L | M
| Historical data 历史订单 |  |  | M | H
| Receipt 收据 |  |  | L | L
| Product 商品内容 | Hot selling 热销商品 |  | H | M
|  | Product recommendation 商品推荐 |  | M | M
|  | Pre-order 商品订购 |  | L | L
|  | Wish list “我想购买” |  | L | L
| Promotion 商品促销 | Bonus 积分 |  | H | H
|  | Coupon / Voucher 优惠券 |  | H | H
|  | Personalization 个性化 |  | M | L
|  | Invitation 邀请功能 |  | L | L
| Advertisement 广告 | Banner |  | M | M
| Notification 消息推送 | New promotion, new product, new box 新促销活动推送，新商品销售推送，新盒子营业消息推送等 |  | M | M
| Face recogition 人脸识别 | Get into box 人脸识别进出门 |  | M | L
|  | Payment 人脸支付 |  | M | L
| Error handling system 问题处理功能 | Un-paid order 未支付订单 |  | M | H
|  | Cancel order 取消订单 |  | L | L
|  | Unrecognize product 未识别商品-- |  | M
|  | Wrong pricing 价格错误--运营系统 |  | H
|  | Wrong product information 商品信息错误 |  | H
|  | Miscalculation 商品数量计算错误 |  | H
| Help 用户引导/帮忙 | Instruction App使用引导页与说明 |  | M | M
Note on C10: pangyixin: Please give specific situations
Note on C12: Microsoft Office User: Currently this function is provided by Xiaoyu, and SCG wants to find a local replacement.
Note on C25: pangyixin: Removed since this item is already implemented in "Good receive"
Note on C34: pangyixin: Removed since this item is already implemented in "Stock availability"
Note on C41: pangyixin: Removed since users will not show any QR code to the ashier.
Note on C42: pangyixin: Removed since users will not show any QR code to the cashier.
Note on C46: pangyixin: Window 10 has mandatory auto update , which might affects customer check out. Let's consider to move on new OS (possibly Linux), or buy enterprise license for Windows 7.
Note on C56: pangyixin: Please explain it in detail
Note on C59: pangyixin: Please explain in detail
Note on C67: pangyixin: We do not really suggest to check CCTV online on mobile APP, since developing such an App with high speed video streams could cost a lot. Moreover, uploading videos from boxes could occupy huge bandwidth of Box's internet (0.5MB/s for each camera), which might affect the checkout process.
Note on C70: Microsoft Office User: Currently this function is provided by Xiaoyu, and SCG wants to find a local replacement.
Note on C75: pangyixin: Please explain it
Note on C93: pangyixin: Separate areas are needed for this business, since user need to fetch their goods at some place.
Note on C97: pangyixin: Are you talking about personalized recommendation? A recommendation system ready for commerical usage would cost enormous amounts of money and time (see Google/Facebook/Alibaba) and thus cannot be accomplished in development at current scale.
Note on C105: pangyixin: User should not see this on their App, and this information should be recorded on OPS.
Note on C106: pangyixin: User should not see this on their App, and this information should be recorded on OPS.
Note on C107: pangyixin: User should not see this on their App, and this information should be recorded on OPS.
Note on C108: pangyixin: User should not see this on their App, and this information should be recorded on OPS.

## meeting result -12月12日讨论后表格
|  | *红色为12月12日开会讨论后的内容 Red one represents the update content after 12 Dec |  | B-tree: H=<3, M=<6, L=<12 M
Module | Function |  | Explanation | SCG suggested Priority (H/M/L) | B-Tree suggested Priority (H/M/L)
OPS/运管系统
User 用户 | User management 用户管理 | Add/update/delete user 人员管理：新增、更新、删除 | To Operators/针对运营人员 | H | H
|  | Password management 密码管理 | To Operators/针对运营人员 | H | H
|  | Role Permission 角色管理/权限管理 | To Operators/针对运营人员 | H | H
Box 盒子 | Box management 运营盒子管理 | Add/delete box 增加/删除盒子 |  | H | H
|  | Suspend box = Box status 盒子运营管理：待业、营业、停业、暂停营业 |  | H | H
|  | Location 盒子位置 |  | H | H
|  | Emergency handling-- 盒子紧急故障处理 |  | H | H
|  | Price Tag Electronics 电子价签 | Depends on PT hardwards/依赖于电子价签硬件 | M | L
|  | Advertising VDO 视频广告管理，可根据需要设置广告视频播放内容 |  | M | L
Commodity 商品 | Commodity 商品管理 | Add/update/delete product 商品增加、删除、更新 | To Products List/针对商品列表 | H | H
|  | Category 商品目录，针对泰国商品可配置 |  | H | H
|  | Hold product 商品库存管理 |  | H | H
|  | Maintain pricing 商品价格管理 * Price adjustment (advance) / 定时定价策略(烟酒类商品） |  | H | H
| Purchase order 采购管理 | Supplier Manage：Add/update/delete 供应商管理：新增、更新、删除 |  | H | H
|  | Costing by Supplier 供应商商品及进价管理 |  | H | H
|  | Purchase order process* ( Add Product … ) 进货订单/退货订单处理 |  | H | H
| Warehouse management 库存管理 | Stock availability 有效商品库存 |  | H | H
|  | Min stock 最小商品库存。用于安全库存报警，及时采购和补货 |  | H | H
|  | Reorder 重复订购 |  | H | H
|  | Good receive 商品入库 |  | H | H
|  | Good issue 入库商品问题处理 |  | H | H
| 同意移除此项重复的功能 SCG agree to remove this repeated function | Inventory count 商品出入库数量 |  | H | H
|  | Damage/loss handling 盘点：盘亏/盘盈 | Connected with financial system/连接到财务系统 | H | H
|  | Stock adjustment 库存调整 | Connected with financial system/连接到财务系统 | H | H
| Return management 退货管理 | Return to supplier 退货(至供应商) | Option 1: Box return goods to supplier directly Option 2: Box return goods to warehouse, then warehouse return goods to supplier | H | H
| Inventory management 进销存管理（盒子） | Stock availability 盒子有效商品库存 |  | H | H
|  | Min stock 盒子最小库存 |  | H | H
|  | Reorder 盒子商品重复订购 |  | H | H
|  | Good receive 商品入盒 |  | H | H
|  | Good issue 入盒商品问题处理 |  | H | H
| 同意移除此项重复的功能 SCG agree to remove this repeated function | Inventory count 商品库存 |  | H | H
|  | Damage/loss handling 盘点：盘亏/盘盈 |  | H | H
|  | Stock adjustment 商品库存微调 |  | H | H
Promotion 促销 | Promotion 促销 | Discount 折扣 |  | H | H
|  | Coupon 积分 |  | M | M
|  | Bonus 优惠券 |  | M | M
|  | Buy 1 Get 1 free : Get 2 Get 3 Get … 买1送N |  | H | H
| 需求:希望一个二维码可支持app会员支付 和第三方支付, 等待确认具体需求 SCG’s requirement: expect one QR code can support membership payment and third party payment, B-tree is waiting for confirm detail requirement. Before we give confirmed answer that whether one QR code can supports S-Bingobox app payment with discount and other app payment, we need to confirm following questions: 1. Please confirm which thirty payment you would like to add? 2. Which payments are included in the S-bingobox app? when user pay the order, S-Bingobox app will trigger and open third party app, then make the payment, just like Chinese payment process. 3. Please offer relevant API files of thirty party payment Because some apps have interfaces for external connections, while others are not. | QR Promotion Discount |  | M
|  | Member Price by individual QR Code |  | M
|  | Limited Time by Product Ex. ALH 限时限价促销商品 |  | H | H
Financial Part 财务 | API Management 第三方系统对接 | Plug in with Netsuite 支持与SCG所用ERP系统（Netsuite）进行系统对接 |  | H | H
Owen | Owen function Owen相关 | Update program 收银软件更新 |  | H | M
| 已达成共识,先进行开发,后期慢慢变成linux操作系统 Two parties reach a consensus that developing window first, then convert to Linus | Support OS Window 10 支持Windows10 |  | H | M
|  | *Barcode management 增加Barcode识别功能，增强商品销售 |  | L | L
Security 商品防盗 | Security 商品防盗 | AM Tag AM标签 |  | H | H
Report 报告 | Transaction report 销售订单报告 | Daily, monthly 日报/月报 |  | H | M
Two parties reach a consensus that finish this function within 6 months |  | By location, By product category, By supplier 根据盒子/区域，商品分类，供应商等条件生成报告 |  | H | M
|  | Basket size, Avg. THB/bill 均单商品数，均单消费金额 |  | H | M
| Financial report 财务报告 | Revenue, Cost, Margin 收入报告、成本报告、毛利润报告 |  | H | M
|  | By location, By product category, By supplier 根据盒子/区域，商品分类，供应商等条件生成报告 |  | H | M
| Inventory report 进销存报告 | Stock 库存报告 |  | H | M
|  | Turnover 商品流转率 |  | H | M
waiting confirm the sales content of table 商品按时间段（如月度）的销售量 |  | High/medium/slow move 高/中/低流转商品报告 |  | H | M
|  | Shelf life 商品保质期 |  | H | M
| Customer report 顾客报告 | Retention 顾客留存数据报告。顾客频次，回头率等 |  | M | M
|  | Personal; gender, demographic, spending 包含顾客数据：性别、国籍/地区、消费金额等 | 我们能提供什么信息,他们想要的信息 | M | M
| Customer support 客服报告 | Customer Incident report 客服问题处理报告 |  | H | M
| Operation Report 运营报告 | Operation Resolve report 运营问题处理报告。系统故障，运营故障等 |  | H | M
Language 系统语言 |  | English 英文支持 |  | H | H
Customer Service/客服系统
| Camera system 监控CCTV | Monitor 摄像头 | Not sure whether or not will we replace the entire CCTV module/不确定是否更换整个CCTV模块 | H | H
|  | Detection 人物动帧检测 | Depends on CCTV module/依赖于CCTV模块 | H | H
|  | Video playback 监控视频回放 | Depends on CCTV module/依赖于CCTV模块 | H | H
|  | APP Mobile 移动端视频查看功能 |  | H | M
| Blacklist 顾客黑名单 |  | To Customers/针对顾客 | H | H
| Logging system 客服日志系统 | Logging incident 客服日志系统 |  | H | M
| Call handling 客服呼叫调度 | 客服中心呼叫自动调度功能，多线顾客呼叫自动分配给不同客服 This function relate to Xiaoyu, SCG want to find local accessory to replace it. |  | H | L
| Remote control system 远程控制系统 | Communication with customer 语音/视频通话功能，与顾客进行通话 |  | H | H
|  | Open/Lock door remotely 远程开/关门 |  | H | H
|  | Control owen system; fix issue, restart system 远程控制Owen，解决问题，重启软件/PC |  | H | H
|  | Set alarm 与盒子里顾客通信，紧急情况下可呼叫到盒子并警告顾客 | Depends on hardwares/依赖于硬件 Now one can use video calls on screens inside boxes/目前可直接使用语音/视频电话接入到盒子内来实现 | H | M
|  | *Owen？？？?? |  | H
App/移动端
App | Register 注册 | By email, mobile no. 注册方式：E-Mail，手机号 |  | H | H
|  | OTP generation 短信验证 |  | H | H
| Login 登录 | Password Login 密码登录 |  | H | H
| Password management 密码管理 | Change/reset/forgot password * 修改密码 * 忘记密码找回 |  | H | H
| Opening door 开门 | QR Opening Door 扫码开门 |  | H | H
| Payment 支持方式 | TH QR |  | H | H
|  | ALIPAY |  | M | M
|  | LINE PAY |  | H | H
|  | Credit QR |  | H | H
|  | Face Payment 人脸支付 | Needs supports from hardwares/需要硬件设备支持 | M | L
| Search box 搜索附近的盒子 |  |  | L | M
| Search product availability 搜索盒子里商品 |  |  | L | M
| Historical data 历史订单 |  |  | M | H
| Receipt 收据 |  |  | L | L
| Product 商品内容 | Hot selling 热销商品 |  | H | M
|  | Product recommendation 商品推荐 |  | M | M
|  | Pre-order 商品订购 |  | L | L
|  | Wish list “我想购买” |  | L | L
| Promotion 商品促销 | Bonus 积分 |  | H | H
|  | Coupon / Voucher 优惠券 |  | H | H
|  | Personalization 个性化 |  | M | L
|  | Invitation 邀请功能 |  | L | L
| Advertisement 广告 | Banner |  | M | M
| Notification 消息推送 | New promotion, new product, new box 新促销活动推送，新商品销售推送，新盒子营业消息推送等 |  | M | M
| Face recogition 人脸识别 | Get into box 人脸识别进出门 |  | M | L
|  | Payment 人脸支付 |  | M | L
| Error handling system 问题处理功能 | Un-paid order 未支付订单 |  | M | H
|  | Cancel order 取消订单 |  | L | L
|  | Unrecognize product 未识别商品-- |  | M
|  | Wrong pricing 价格错误--运营系统 |  | H
|  | Wrong product information 商品信息错误 |  | H
|  | Miscalculation 商品数量计算错误 |  | H
| Help 用户引导/帮忙 | Instruction App使用引导页与说明 |  | M | M
Note on C10: pangyixin: Please give specific situations
Note on C12: Microsoft Office User: Currently this function is provided by Xiaoyu, and SCG wants to find a local replacement.
Note on C25: pangyixin: Removed since this item is already implemented in "Good receive"
Note on C34: pangyixin: Removed since this item is already implemented in "Stock availability"
Note on C41: pangyixin: Removed since users will not show any QR code to the ashier.
Note on C42: pangyixin: Removed since users will not show any QR code to the cashier.
Note on C46: pangyixin: Window 10 has mandatory auto update , which might affects customer check out. Let's consider to move on new OS (possibly Linux), or buy enterprise license for Windows 7.
Note on C56: pangyixin: Please explain it in detail
Note on C59: pangyixin: Please explain in detail
Note on C67: pangyixin: We do not really suggest to check CCTV online on mobile APP, since developing such an App with high speed video streams could cost a lot. Moreover, uploading videos from boxes could occupy huge bandwidth of Box's internet (0.5MB/s for each camera), which might affect the checkout process.
Note on C70: Microsoft Office User: Currently this function is provided by Xiaoyu, and SCG wants to find a local replacement.
Note on C75: pangyixin: Please explain it
Note on C93: pangyixin: Separate areas are needed for this business, since user need to fetch their goods at some place.
Note on C97: pangyixin: Are you talking about personalized recommendation? A recommendation system ready for commerical usage would cost enormous amounts of money and time (see Google/Facebook/Alibaba) and thus cannot be accomplished in development at current scale.
Note on C105: pangyixin: User should not see this on their App, and this information should be recorded on OPS.
Note on C106: pangyixin: User should not see this on their App, and this information should be recorded on OPS.
Note on C107: pangyixin: User should not see this on their App, and this information should be recorded on OPS.
Note on C108: pangyixin: User should not see this on their App, and this information should be recorded on OPS.

## OPS功能清单
Module | Function |  | Explanation | SCG suggested Priority (H/M/L) | B-Tree suggested Priority (H/M/L) | 说明
OPS/运管系统
User 用户 | User management 用户管理 | Add/update/delete user 人员管理：新增、更新、删除 | To Operators/针对运营人员 | H | H
|  | Password management 密码管理 | To Operators/针对运营人员 | H | H
|  | Role Permission 角色管理/权限管理 | To Operators/针对运营人员 | H | H
Box 盒子 | Box management 运营盒子管理 | Add/delete box 增加/删除盒子 |  | H | H
|  | Suspend box = Box status 盒子运营管理：待业、营业、停业、暂停营业 |  | H | H
|  | Location 盒子位置 |  | H | H
|  | Emergency handling-- 盒子紧急故障处理 |  | H | H
|  | Price Tag Electronics 电子价签 | Depends on PT hardwards/依赖于电子价签硬件 | M | L
|  | Advertising VDO 视频广告管理，可根据需要设置广告视频播放内容 |  | M | L
Commodity 商品 | Security 商品防盗 | AM Tag AM标签 |  | H | H
| Commodity 商品管理 | Add/update/delete product 商品增加、删除、更新 | To Products List/针对商品列表 | H | H
|  | Category 商品目录，针对泰国商品可配置 |  | H | H
|  | Hold product 商品库存管理 |  | H | H
|  | Maintain pricing 商品价格管理 * Price adjustment (advance) / 定时定价策略(烟酒类商品） |  | H | H
| Purchase order 采购管理 | Supplier Manage：Add/update/delete 供应商管理：新增、更新、删除 |  | H | H
|  | Costing by Supplier 供应商商品及进价管理 |  | H | H
|  | Purchase order process* ( Add Product … ) 进货订单/退货订单处理 |  | H | H
| Warehouse management 库存管理 | Stock availability 有效商品库存 |  | H | H
|  | Min stock 最小商品库存。用于安全库存报警，及时采购和补货 |  | H | H
|  | Reorder 重复订购 |  | H | H
|  | Good receive 商品入库 |  | H | H
|  | Good issue 入库商品问题处理 |  | H | H
|  | Damage/loss handling 盘点：盘亏/盘盈 | Connected with financial system/连接到财务系统 | H | H
|  | Stock adjustment 库存调整 | Connected with financial system/连接到财务系统 | H | H
| Return management 退货管理 | Return to supplier 退货(至供应商) | Option 1: Box return goods to supplier directly Option 2: Box return goods to warehouse, then warehouse return goods to supplier | H | H
| Inventory management 进销存管理（盒子） | Stock availability 盒子有效商品库存 |  | H | H
|  | Min stock 盒子最小库存 |  | H | H
|  | Reorder 盒子商品重复订购 |  | H | H
|  | Good receive 商品入盒 |  | H | H
|  | Good issue 入盒商品问题处理 |  | H | H
|  | Damage/loss handling 盘点：盘亏/盘盈 |  | H | H
|  | Stock adjustment 商品库存微调 |  | H | H
Promotion 促销 | Promotion 促销 | Discount 折扣 |  | H | H
|  | Coupon 积分 |  | M | M
|  | Bonus 优惠券 |  | M | M
|  | Buy 1 Get 1 free : Get 2 Get 3 Get … 买1送N |  | H | H
|  | Limited Time by Product Ex. ALH 限时限价促销商品 |  | H | H
Financial Part 财务 | API Management 第三方系统对接 | Plug in with Netsuite 支持与SCG所用ERP系统（Netsuite）进行系统对接 |  | H | H
Report 报告 | Transaction report 销售订单报告 | Daily, monthly 日报/月报 |  | H | M | Two parties reach a consensus that finish this function within 6 months
|  | By location, By product category, By supplier 根据盒子/区域，商品分类，供应商等条件生成报告 |  | H | M
|  | Basket size, Avg. THB/bill 均单商品数，均单消费金额 |  | H | M
| Financial report 财务报告 | Revenue, Cost, Margin 收入报告、成本报告、毛利润报告 |  | H | M
|  | By location, By product category, By supplier 根据盒子/区域，商品分类，供应商等条件生成报告 |  | H | M
| Inventory report 进销存报告 | Stock 库存报告 |  | H | M
|  | Turnover 商品流转率 |  | H | M
|  | High/medium/slow move 高/中/低流转商品报告 |  | H | M | waiting confirm the sales content of table 商品按时间段（如月度）的销售量
|  | Shelf life 商品保质期 |  | H | M
| Customer report 顾客报告 | Retention 顾客留存数据报告。顾客频次，回头率等 |  | M | M
|  | Personal; gender, demographic, spending 包含顾客数据：性别、国籍/地区、消费金额等 | 我们能提供什么信息,他们想要的信息 | M | M
| Customer support 客服报告 | Customer Incident report 客服问题处理报告 |  | H | M
| Operation Report 运营报告 | Operation Resolve report 运营问题处理报告。系统故障，运营故障等 |  | H | M
Language 系统语言 |  | English 英文支持 |  | H | H
收银台
Owen | Owen function Owen相关 | Update program 收银软件更新 |  | H | M | 硬件(收银台)
|  | *Barcode management 增加Barcode识别功能，增强商品销售 |  | L | L
Customer Service/客服系统
Camera system 监控CCTV | Camera system 监控CCTV | Monitor 摄像头 | Not sure whether or not will we replace the entire CCTV module/不确定是否更换整个CCTV模块 | H | H
|  | Detection 人物动帧检测 | Depends on CCTV module/依赖于CCTV模块 | H | H
|  | Video playback 监控视频回放 | Depends on CCTV module/依赖于CCTV模块 | H | H
|  | APP Mobile 移动端视频查看功能 |  | H | M
客户管理 | Blacklist 顾客黑名单 |  | To Customers/针对顾客 | H | H
| Logging system 客服日志系统 | Logging incident 客服日志系统 |  | H | M
| Call handling 客服呼叫调度 | 客服中心呼叫自动调度功能，多线顾客呼叫自动分配给不同客服 This function relate to Xiaoyu, SCG want to find local accessory to replace it. |  | H | L
Remote control system 远程控制系统管理 | Remote control system 远程控制系统 | Communication with customer 语音/视频通话功能，与顾客进行通话 |  | H | H
|  | Open/Lock door remotely 远程开/关门 |  | H | H
|  | Control owen system; fix issue, restart system 远程控制Owen，解决问题，重启软件/PC |  | H | H
|  | Set alarm 与盒子里顾客通信，紧急情况下可呼叫到盒子并警告顾客 | Depends on hardwares/依赖于硬件 Now one can use video calls on screens inside boxes/目前可直接使用语音/视频电话接入到盒子内来实现 | H | M
App/移动端
用户管理 | Register 注册 | By email, mobile no. 注册方式：E-Mail，手机号 |  | H | H
|  | OTP generation 短信验证 |  | H | H
| Login 登录 | Password Login 密码登录 |  | H | H
| Password management 密码管理 | Change/reset/forgot password * 修改密码 * 忘记密码找回 |  | H | H
| Opening door 开门 | QR Opening Door 扫码开门 |  | H | H
首页 | Advertisement 广告 | Banner |  | M | M
| Notification 消息推送 | New promotion, new product, new box 新促销活动推送，新商品销售推送，新盒子营业消息推送等 |  | M | M
盒子管理 | Search box 搜索附近的盒子 |  |  | L | M
| Search product availability 搜索盒子里商品 |  |  | L | M
| Face recogition 人脸识别 | Get into box 人脸识别进出门 |  | M | L
|  | Payment 人脸支付 |  | M | L
商品管理 | Product 商品内容 | Hot selling 热销商品 |  | H | M
|  | Product recommendation 商品推荐 |  | M | M
|  | Wish list “我想购买” |  | L | L
| Promotion 商品促销 | Bonus 积分 |  | H | H
|  | Coupon / Voucher 优惠券 |  | H | H
|  | Invitation 邀请功能 |  | L | L
我的订单 | Historical data 历史订单 |  |  | M | H
| Receipt 收据 |  |  | L | L
| Error handling system 问题处理功能 | Un-paid order 未支付订单 |  | M | H
|  |  |  | L | L
支付管理 | Payment 支持方式 | TH QR |  | H | H
|  | ALIPAY |  | M | M
|  | LINE PAY |  | H | H
|  | Credit QR |  | H | H
|  | Face Payment 人脸支付 | Needs supports from hardwares/需要硬件设备支持 | M | L
用户帮助 | Help 用户引导/帮忙 | Instruction App使用引导页与说明 |  | M | M
Note on C9: pangyixin: Please give specific situations
Note on C11: Microsoft Office User: Currently this function is provided by Xiaoyu, and SCG wants to find a local replacement.
Note on C48: pangyixin: Please explain it in detail
Note on C51: pangyixin: Please explain in detail
Note on C62: pangyixin: We do not really suggest to check CCTV online on mobile APP, since developing such an App with high speed video streams could cost a lot. Moreover, uploading videos from boxes could occupy huge bandwidth of Box's internet (0.5MB/s for each camera), which might affect the checkout process.
Note on C65: Microsoft Office User: Currently this function is provided by Xiaoyu, and SCG wants to find a local replacement.